## Requrenments
# | Requirements | Priority
1 | Color code for specific indication | High
2 | Small in size | High
3 | Good aesthetic view | Low

## Project Plan
# | Task Name | Resource | Duration (hr) | Start | Finish | % Complete | Comments
1 | User Stories
1.2 | User Story workshops | Project Manager | 0.3 | 2021-01-08 | 2021-01-08 | 100%
1.3 | User Stories Walk-through and sign off | Project Manager | 0.3
2 | Product Backlog
2.1 | Create Product Backlog | Project Manager | 0.3 | 2021-01-08 | 2021-01-08 | 100%
2.2 | Story Estimation | Project Team | 0.2
2.3 | Prioritize | Project Manager | 0.1
3 | Sprint-0
3.1 | Create project timeline | Project Manager | 0.1 | 2021-01-08 | 2021-01-08 | 100%
3.2 | Draft resource plan | Project Manager | 0.1
3.3 | Plan project budget | Project Manager | 0.1
4 | Sprint - 1 (Circuit Design)
4.1 | Circuit Design On Paper | Project Team | 0.3 | 2021-01-09 | 2021-01-09 | 100%
4.2 | Circuit Design Simulation | Project Team | 0.3
4.3 | Circuit Design on Bread-Board | Project Team | 0.1
5 | Sprint - 2 (PCB Design)
5.1 | Design PCB on CAD Software (Protious) | Project Team | 0.1 | 2021-01-09 | 2021-01-09 | 100%
5.2 | Actual PCB making | Project Team | 1
6 | Sprint - 3 (Testing and Review )
6.1 | Testing according to user stories | Project Team | 0.2 | 2021-01-10 | 2021-01-10 | 100%
6.2 | Review Design | Project Team | 0.1
6.3 | Deliverable or implementable prototype enclosure | Project Team | 0
| Total Time |  | 3.6

## Product backlog
Product Backlog
Details | [5 empty] | Team
Epic | Sprint | User Story Role | User Story Name | Story Details | Acceptance Test Criteria | How to Demo | Tasks | Sub-Task | Analyst / Prep work
Tester Insertion | 2 | USB port has defect | Connects USB Tester to hardware | Gets Green light from tester as output reading | 1. Green LED glows which indicates power port of USB is OK. |  | 1. Remove the USB Tester from socket | none | 1
Tester Insertion | 2 | USB port has no defect | Connects USB Tester to hardware | Gets Red light from tester as output reading | 1. Red LED glows which indicates power port of USB has some defect. |  | 1. Remove the USB Tester from socket 2. Check ether Blue light is also glowing . | 1. Blue light glow indicates that the data line has some defect. | 2

## Sprint plan
Milestones/Deliverables | Sprint 1(8 Jan 2021) | Sprint2(9 Jan 2021) | Sprint3(10 Jan 2021)
First Half Milestones | USB analysis : -> Study USB and it's uses -> Design circuit diagram on paper | PCB Design on Software : | Component Mounting
Second Half Milestones | Circuit Design : -> Calculation on paper -> Implementation of circuit design in Simulation | PCB Design in real hardware | Testing Output product
Third Half Milestone | Circuit Design : -> Implementation of circuit design on bread board | Testing PCB Design | Final working product

## Task List
Sprint | Description | Task | Sub-Task | Assigned to | Estimate Time (hr) | Time Taken (hr) | Status | Remarks
0 | Product Backlog | 1. Project Study | 0.1.1. Literature Survey | Siddhant Joshi | 0.3 | 0.3 | Complete
|  |  | 0.1.2. Changes in Existing System | Siddhant Joshi |  |  | Complete
|  |  | 0.1.3. Analyzing Drawbacks | Siddhant Joshi |  |  | Complete
|  |  | 0.1.4. Existing System Present | Siddhant Joshi |  |  | Complete
|  |  | 0.1.5. Virtual System Implementation | Siddhant Joshi |  |  | Complete
|  | 2. Understanding Industrial Methods | 0.2.1. Agile Methodology Study | Siddhant Joshi |  |  | Complete
|  |  | 0.2.1. Scrum Methodology | Siddhant Joshi |  |  | Complete
|  | 3. User Story | 0.3.1. Forming User Stories | Siddhant Joshi |  |  | Complete
|  |  | 0.3.2. System Use Cases | Siddhant Joshi |  |  | Complete
|  | 4. Sprint Planning | 0.4.1. Defining Sprints | Siddhant Joshi |  |  | Complete
|  |  | 0.4.2. Assigning Tasks | Siddhant Joshi |  |  | Complete
1 | Circuit Design | 1. Components Study | 1.1.0 Connection of USB | Siddhant Joshi | 1.5 | 1.5 | Complete
|  |  | 1.1.1 Basic of Electronics Resistor | Siddhant Joshi |  |  | Complete
|  |  | 1.1.2 Basic of Electronics LED | Siddhant Joshi |  |  | Complete
|  | 2. Software Study | 1.2.0 Learn Protious Schematic Diagram design | Siddhant Joshi |  |  | Complete
|  |  | 1.2.1 Learn Protious PCB design | Siddhant Joshi |  |  | Complete
|  | 3. Design Circuit | 1.3.0 Design Circuit on Paper | Siddhant Joshi |  |  | Complete
|  |  | 1.3.1 Design Circuit on protious | Siddhant Joshi |  |  | Complete
|  |  | 1.3.2 Design Circuit on Bread Board | Siddhant Joshi |  |  | Complete
2 | PCB Design | 1. Design PCB | 2.1.0 Design PCB on Protious | Siddhant Joshi | 1.1 | 1.1 | Complete
|  |  | 2.1.1 Move PCB from Paper to Epoxy sheet with plated copper | Siddhant Joshi |  |  | Complete
|  | 2. Testing PCB | 2.2.0 Testing PCB | Siddhant Joshi |  |  | Complete
3 | Testing and Review | 1. Testing according to user stories | 3.1.0 PCB Testing in actual environment | Siddhant Joshi | 30 | 30 | Complete
|  |  | 3.1.1 Flaws Finding and solving | Siddhant Joshi |  |  | Complete
|  |  | 3.1.2 Enclosure | Siddhant Joshi |  |  | Complete